## ESB WKLY RPT-01-28 thru 02-03
Technology Shared Services and Pharmacy - Weekly Status & Milestones - 1/28/2016 - 2/3/2016
Area | Item | Description | EMT Member | R,Y,G | Key Issues | Key Accomplishments/Comments
OPPR/ESB | Production Monitoring | 1. Production QMON and Incident related to QMONs for all the regions. 2. Production Applications monitoring 3. Production server health monitoring and support 4. All production reports (daily) published to the users | Ash/Neeraj | G | No Issues | 1. SIG reports generated and published to Users 2. Daily IVR/UTP Orders/UTP Allergy reports published to the users
OPPR/ESB | Non Prod Monitoring | 1. Monitor the Non Production environment for all the WAS servers, WMB Servers, DB connections and the applications deployed to avoid the BAT defects | Ash/Neeraj | G | No Issues | Non prod environment check and validation before start of the PTQ testing completed everyday.
OPPR/ESB | Non Production | 1. Defects were addressed and resolved/reassigned accordingly | Ash/Neeraj | G | No Issues | Number of Defects addressed for the week : 85
OPPR/ESB | Production Support | 1. Production Incidents triage | Ash/Neeraj | G | No Issues | Critical/High incidents - NONE Total Medium/Low incidents addressed for the week : 284
OPPR/ESB | Production Deployments | 1. EPS R 4.1 Patch 5 - SCAL 2. NCAL Cutover - Diablo 1 3. EPS R 4.1 Patch 5 - NCAL 4. HI New Store (6026) ESB Set up/cutover 5. EPS R 4.1 Patch 5 - CO/GA | Ash/Neeraj | G | No Issues | EPS R4.1 Patch 5 upgrade for SCAL(1/28), NCAL(2/1), CO&GA (2/3) completed successfully Diablo 1 - NCAL Cutover - Completed - 1/29&1/30 HI New store 6026 setup/cutover - Completed - 2/2
OPPR/ESB | Non Prod Deployments | 1. Completed 17 non-prod deployments a. CERT = 4 deployments b. QA1 = 6 deployments c. QA2 = 5 deployments d. PSUP = 2 deployments | Ash/Neeraj | G | No Issues | CERT Deployments: 1. DE3638 : IntellicabRxListener R5.1 2. US17440 : Three Node Architecture : Deploy R5 SG1 and R5 KPRXRoutingListener for 3 node architecture 3. For US17712 : ESBRxService R6 4. US17846 : IntellicabRxListener R5.1 : CERT Deployment QA1 Deployments: 1. WO0000006283961 - US 17237, 17048, 17308, 17309, 17118 : Mobile App MDFA US Deployment 2. WO0000006284420 - QC 22507: PERC Max Day Verbiage is not consistent 3. WO0000006284915 - QC22437 : PERC Reports are not displaying properly when running in CSV format 4. WO0000006285113 - QC22691 : National Mail Order Receipt to QA1, CR254 - Missing Verbiage 5. WO0000006287378 - ESB support for Start to Stop KPHC to EPS flow to create test data as part of CR299 6. WO0000006307950-US17567 to deploy the Thermal Labels CA V3.8 and ROC v3.6 QA2 Deployments: 1. WO0000006267427-settings required at ESB side QA2 SCAL 2. WO0000006284976 - DEA Flag to be Turned OFF at ESB for SCAL and CO region during offshore hours 3. WO0000006285498 - Set the Time frame at back-end for the respective test termiated prescriber for testing R5.1 US11753 4. WO0000006307949-US 15403/4:Benefit ESB FS EIS NCA Member Eligibility Service Transition from V2 to V3[CR348] 5. WO0000006308138-Request to repoint PTQ NW stores 4010 to QA2 PSUP Deployments: 1. WO0000006261893-NW PSUP Env - ESB WAS Server Certificate update 2. CRQ000000371100 - PSUP CS & SCAL R5 Upgarde
OPPR/ESB | Automation | 1. UCD (Urban Code Deployment) for automating production/non-prod deployments | Ash/Neeraj | G | No Issues | App deployment via UCD for : a. Dev3/QA3 - In progress b. PSUP2 - In progress
Upcoming Milestones Planned
Area | Item | Planned milestone date
OPPR/ESB | EPS R 4.1 Patch 5 - NW/MA | 2016-02-04
OPPR/ESB | NCAL Cutover - Diablo 2 | 2/5/2016 & 2/6/2016
OPPR/ESB | EPS R 4.1 Patch 5 - HI | 2016-02-08
OPPR/ESB | R5 Pilot - SCAL + SCAL ESB R5 Go Live + CS Upgrade | 2/8/2016 & 2/9/2016
OPPR/ESB | CCS TI Go Live - CO/HI/GA | 2016-02-10
OPPR/ESB | R5 Golive for EPS Stores # 1- SCAL | 2016-02-12
OPPR/ESB | R5 Golive for EPS Stores # 2- SCAL + SCAL ESB R5 IVR/KP.ORG Go Live | 2016-02-16
OPPR/ESB | R5 Pilot - GA | 2016-02-16
OPPR/ESB | R5 Pilot - HI + HI ESB R5 Go Live | 2016-02-16
OPPR/ESB | NCAL Cutover - SFO | 2/19/2016 & 2/20/2016
OPPR/ESB | ECIMS Go Live - SCAL | 2/19/2016 or 2/22/2016
OPPR/ESB | R5 Golive for EPS Stores - HI + HI ESB R5 IVR/KP.ORG Go Live | 2016-02-22
OPPR/ESB | R5 Pilot - MAS + MAS ESB R5 Go Live | 2016-02-22
OPPR/ESB | 2/23 - ESB Maint Release & Patch 5 Deployment Support - CR 255 MSAI V2 - DE 21956 - CR 342 - SBMO/PERC Web Reports | 2016-02-23
OPPR/ESB | ESB Exadata Migration - GA | 2016-02-24
OPPR/ESB | R5 Golive for EPS Stores - MAS + MAS ESB R5 IVR/KP.ORG Go Live | 2016-02-25