## owssvr(1)
ID | Title | Project# | Created | Due Date | Sub Area | Priority | Issue Status | Assigned To | Escalated To | Flag for Program Integration Meeting | Flag for Exec Mtg | R/Y/G Status | Escalation Action Required | Situation and Background | Assessment and Recommendation | Update Log | Created By | Modified | Modified By | Flag for KP-PDX Meeting | Status Report Update | Path
3 | PHI Encryption - Direction for OPPR | xxxxx-PnS | 2011-11-29 11:49 | 2011-12-02 | Compliance | High | Active | Bhattacharya, Apurba X | Ashish Tengshe | Yes | No | Red |  | OPPR Lacks a program level decision about whether or not to encrypt PHI data being transmitted across various applications | POS architecture has been un-necessarily designed to handle encryption of PHI data causing severe performance issue. Also, getting read of SafeNet interface requires major code changes if POS needs to continue to encrypt PHI data The recommendatation is that the Program should come up with a waiver for PHI encryption. | 1/19 PHI all-day meeting led by Deb Barnett | Bhattacharya, Apurba X | 2012-01-24 11:47 | Michelle A. Sullivan | No |  | sites/OPPR/Sprints/Lists/Technology Team Issues Log
1 | External entities having controll on ePIMS/ePOS hardware | 08871-POS | 2011-11-23 12:11 | 2011-12-16 | Compliance | High | Active | Jeffrey Raymond Poole | Ashish Tengshe | Yes | No | Red | Have those groups publish a schedule of such changes and have them work with each application team to properly test it before deployment | External entities have some sort of control on the ePIMS/ePOS workstations, peripherals, and Servers. | Due to such control, new and untested softwares are being deployed on workstations and Servers causing application program to fail. | 12/02: Assigned to Jeff's correct ID. 11/23 :- Initiated conversion with Compliance officer and notified that such changes are severely affecting application functionalities. 1/13: Bring teams together and discuss . Apurba created recommendations and will provide list of teams. Utilize CAB 1/20 : Learned about new security initiatives that may severely impact our applications running in the Pharmacy | Bhattacharya, Apurba X | 2012-01-20 12:38 | Bhattacharya, Apurba X | No |  | sites/OPPR/Sprints/Lists/Technology Team Issues Log
20 | POS work as a result of Websphere upgrade | 08871-POS | 2011-12-16 12:49 | 2011-12-30 | Technology Upgrade | High | Active | Jeffrey Raymond Poole | Ashish Tengshe | No | No | Red |  | There is no process in place to address the impact of technology changes on pharmacy applications. IBM will stop supporting WAS version 6 starting Q2 of 2012. This may have significant impact on how POS application works today | Oracle confirmed that POS application is not certified to work in WAS 7.0. A separate POS project needs to be initiated to understand the impact, plan for remediation, and execute it to ensure business is not impacted. | Emails sent to keep the stakeholders in loop 1/6 - Meeting with Infrastructure team to make progress and Oracle in Austin 2/1. 1/13 - Confirmed WAS 6.0 and 6.1 have support agreement through 9/2013 PCI Compliance is driving upgrade to 7.0 01-20-12 : Draft WAS upgrade strategy created with 3 solution options. Interin review has been scheduled next week | Bhattacharya, Apurba X | 2012-01-20 12:38 | Bhattacharya, Apurba X | No |  | sites/OPPR/Sprints/Lists/Technology Team Issues Log
21 | PMO Issue 327 Citrix-Oracle Issue | xxxxx-Environments | 2012-01-04 15:20 | 2012-01-04 |  | High | Active | Jeffrey Raymond Poole | Jeffrey Raymond Poole | Yes | No | Yellow |  | Citrix is not working with Oracle. | Citrix is not working with Oracle. | Just created | Jeffrey Raymond Poole | 2012-01-13 10:37 | Michelle A. Sullivan | No |  | sites/OPPR/Sprints/Lists/Technology Team Issues Log
26 | WITS Epic NA and OP Bug | xxxxx-Prod Support | 2012-01-20 11:39 | 2012-01-20 |  | High | Active | Jeffrey R. Poole |  | No | No | Red |  | Similar issue to defect 4979 and 4888. Now detected in WITS. | tbd | 1/20 JP | Jeffrey Raymond Poole | 2012-01-27 06:39 | Jeffrey Raymond Poole | No | 1/20 Escalate to KPHC1/27 - the Epic 1/26 prod move was cancelled. KPHC to rollback change on evening of 1/27 | sites/OPPR/Sprints/Lists/Technology Team Issues Log
29 | Defect 4979 and 4888 Epic 2010 (RESC) | xxxxx-Prod Support | 2012-01-20 11:53 | 2012-02-06 | RESC | High | Active | Jeffrey R. Poole |  | No | No | Red |  | Defect 4979 and 4888 Epic 2010 (RESC) returning "KP" instead of "SCA" for NA and OP messages. Affecting pharmacy initiated orders and OP messages. | tbd | 1/20 JP | Jeffrey Raymond Poole | 2012-01-20 11:53 | Jeffrey Raymond Poole | No | 1/20 Escalated to KPHC | sites/OPPR/Sprints/Lists/Technology Team Issues Log
30 | WMB7 needs 2 dedicated LPARs | 19007-ESB Sprints | 2012-01-23 15:23 | 2012-02-10 | Infrastructure | High | Active | Jeffrey Raymond Poole |  | No | No | Yellow |  | Need to have 2 dedicated LPARs to work through WMB upgrade. | Will help sync with the other KP brokers that OPPR connects to. | NA | Michelle A. Sullivan | 2012-01-23 15:23 | Michelle A. Sullivan | No |  | sites/OPPR/Sprints/Lists/Technology Team Issues Log
31 | PDX applications, PDW, POS and KP Infrastructure need to handle timezone offsets correctly | xxxxx-PnS | 2012-01-27 15:28 | 2012-03-30 | Data Warehouse, POS, Infrastructure | High | Active | Ghalib N. Kassam |  | Yes | No | Yellow |  | Critical to ROC Rel and SCAL DR implementation. Per Micahel Herman - I verbally confirmed with PDX today that they use the OS Sys date/time for the client application (EPS and Client). That means East Coast Pharmacy's will have West Coast date and timestamps in the EPS system. I think we better solve this for ROC 1 or GA will be in serious trouble. I am following up with Apurba on how the Oracle POS system is effected by Servers being in Napa - it may be that since we only pull from Central Office they have already figured out timezone issues when servers are centrally located. Once the App is fixed I'll need to understand impact to PDW. I'm facilitating a meeting tomorrow with KP-IT and PDX to go over the questions and see what comes of that. Based on Senthil's responses below I decided I would add Neeraj to the invite. Ash I made you optional. | This issue has been on the tech gaps list for a few months and has been discussed with PDX since the replan last year. The issue/solutions have also been discussed internally with the KP teams during Arch & Governance calls. The plan is to bring this up with PDX during the ROC Rel 1 planning discussion starting next week onwards and get this as a ROC Rel 1 US. While this will resolve the issue with the application (including promise time calculations, scheduling etc.), PDW also needs to look into the date/time across the timezones. Irrespective of whether UTC/TZ offset is used, some of these issue to look at PDW would be, e.g.: Factor in the TZ for the given job/report across the EPS instances e.g. impact on GL processing for Kraemer vs. OH/HI pharmacies. Does the date field need to be normalized across timezones in PDW? Is there a need to run separate jobs for every region or the same job will pull in all the data across the regions? Scheduling of jobs across time zones e.g. store closing Impact on GG processing, etc. Other than the timezone issue, PDW will also need to factor in a way to handle versioning issues for EPS datasets across regions. Even though the goal would be to keep the differences to a minimal, how would the EPS database for GA release compare to the SCAL one? The two datasets will differ for a short time during the transition period.. | We will need to tackle this at both the levels: 1. Understand from PDX, as to why client time will not translate to transaction time. They will also need to factor localization support (for TZ) at the JVM level. 2. DC/infra need to explain - as to why can they not set TZ on a node-by-node basis, and why it did not get factored in as part of the consolidated DC architecture (including DR). I am sure the first response will be - its an app issue, but it needs to be better than that.. | Thangamani X. Vaiyapuri | 2012-01-27 16:27 | Michelle A. Sullivan | No |  | sites/OPPR/Sprints/Lists/Technology Team Issues Log
25 | Inventory Team Dev, QA, & App Support | xxxxx-Prod Support | 2012-01-13 09:55 | 2012-01-19 | Development | Low | Active | Jeffrey Raymond Poole |  | No | No | Yellow |  | Inventory team (Ravi Ravikrishna) is requiring support from development, QA, and Support. | Need strategy to support inventory development and support. Neeraj and Jeff to identify support strategy. | From Ravi Ravikrishna (Inventory team) "Steve is our lead and will make sure we have resources, testers and other support teams are there to make this happen. Steve is business, he does not execute SOAP messages. Steve can execute test scripts using PDX user interface. We need help from your team or Neeraj's team to help us with technical activities ie executing Mock Services, looking into database tables, querying database tables etc. Please let me know who from your team or Neeraj's team will be that person" 1/20 - Scott is now engaged with Ravi's team and will move testing to QA2. | Michelle A. Sullivan | 2012-01-20 11:51 | Jeffrey Raymond Poole | No |  | sites/OPPR/Sprints/Lists/Technology Team Issues Log
10 | WPP does not plans to customize WPP for ROCs | 19007-ESB Sprints | 2011-12-01 11:33 | 2011-10-31 | WPP | Medium | Active | Nasir Ahmad Karamat |  | No | No | Green |  | WPP has not plans of customizing WPP for ROCs. | OPPR to share the ROCs plan | 9/22/2011: WPP team needs plan for ROC and also may need dollars.. | Thangamani X. Vaiyapuri | 2011-12-02 11:13 | Thangamani X. Vaiyapuri | No | 10/28: Neeraj will discuss with Ash/GC - mtg on 10/31 9/26/2011: Request OPPR Leaderhip to have WPP take on ROC customizations. WPP team is looking for tentative OPPR ROC go live dates. | sites/OPPR/Sprints/Lists/Technology Team Issues Log
17 | Re: P7 Acquisition | xxxxx-PnS | 2011-12-01 11:57 | 2011-11-18 | IBM 3rd Party Assessement | Medium | Active | Senthilkumar X. Swaminathan |  | No | No | Green |  | Thomas: This was an item that was raised by Jerry in our last call with GC and Carolyn. Senthil (copied) did tell us that a P7 LPAR has been planned for the PnS environment later in his deployment plan. What we are going to need from the IBM team are the written requirements for the P7. Senthil: I seemed to remember that you mentioned that we "may be" able to accelerate the delivery of the P7 LPAR(s) for PnS and that you would need to work with IBM SO. Can you provide some timeline. Thomas/Sriram: Can the two of you please track this item in your plans such that we have visibility of what is needed and when. As the deliver dates gets closer or is in jeopardy of being missed it can be properly managed? Jerry/Anil: This needs to be an item on our update to GC/Carolyn as to what we did to plan for this "P7 requirement made by IBM" in our last meeting. | Jerry/Anil: This needs to be an item on our update to GC/Carolyn as to what we did to plan for this "P7 requirement made by IBM" in our last meeting. | 11/14: Per Senthil's email: On the P7 build we have ear marked lpars for PnS. However when it will get built is based on the environments team's priority. They are currently building QA2 and it has been their top priority. If we need the P7 for PnS sooner we need to escalate with Jeremey. 9/22/2011: Need an update from Senthil. Thomas/Sriram: Can the two of you please track this item in your plans such that we have visibility of what is needed and when. As the deliver dates gets closer or is in jeopardy of being missed it can be properly managed? | Thangamani X. Vaiyapuri | 2011-12-01 11:57 | Thangamani X. Vaiyapuri | No | 11/14: Per Senthil's email: On the P7 build we have ear marked lpars for PnS. However when it will get built is based on the environments team's priority. They are currently building QA2 and it has been their top priority. If we need the P7 for PnS sooner we need to escalate with Jeremey. | sites/OPPR/Sprints/Lists/Technology Team Issues Log
16 | IBM cannot provide a delivery schedule until a new build process is finalized and introduced with the current dedicated staff. | 19012-Sys Integration | 2011-12-01 11:55 | 2011-12-02 |  | Medium | Active | Melva Jeter |  | No | No | Green |  | IBM cannot provide a delivery schedule until a new build process is finalized and introduced with the current dedicated staff. IBM and KP are collaborating on the build process and a schedule is expected to be delivered in late September. Until such time the team continues to build the infrastructure. | IBM cannot provide a delivery schedule until a new build process is finalized and introduced with the current dedicated staff. IBM and KP are collaborating on the build process and a schedule is expected to be delivered in late September. Until such time the team continues to build the infrastructure. | 11/22: Per Melva: Keep Open - Priority Medium - limited now to WAS (Websphere) staff. New target completion date of 12/31/2011 as we finalize the new RFS for dedicated resources IBM cannot provide a delivery schedule until a new build process is finalized and introduced with the current dedicated staff. IBM and KP are collaborating on the build process and a schedule is expected to be delivered in late September. Until such time the team continues to build the infrastructure. | Thangamani X. Vaiyapuri | 2011-12-01 11:55 | Thangamani X. Vaiyapuri | No | 11/22: Per Melva: Keep Open - Priority Medium - limited now to WAS (Websphere) staff. New target completion date of 12/31/2011 as we finalize the new RFS for dedicated resources | sites/OPPR/Sprints/Lists/Technology Team Issues Log
13 | Home Infusion - Need scope of changes and Target Release | 19007-ESB Sprints | 2011-12-01 11:49 | 2011-12-02 | HI | Medium | Active | Neeraj Pandey |  | No | No | Yellow | None required. Information only at this point for OPPR Exec Mgmt. | ESB Team needs more details on scope of changes, schedule etc so that ESB related changes can be identified and scheduled on sprint cycle. Required to know leadership direction on the target release of the change. |  | 10/28: Ash/Neeraj will meet w/ GC to discuss on next steps 10/27 - At risk of not being able to do SCAL Sprint work (note: this is not going live for SCAL) | Thangamani X. Vaiyapuri | 2011-12-01 11:49 | Thangamani X. Vaiyapuri | No |  | sites/OPPR/Sprints/Lists/Technology Team Issues Log
15 | Contracts with QMSI & Automed | 19009-Implementation | 2011-12-01 11:53 | 2011-12-02 |  | Medium | Active | Subbarao Mulpuru |  | No | No | Green |  | As part of the SBMO effort at the ROCS contracts need to be negotiated with QMSI and Automed. This process is currently underway and this issue is intended to track progress on that effort. | A decision was made to aggregate the contracts across the ROCs in order to obtain some negotiating advantages. Further funding would be taken over by the technology group. | 9-20 gvk - We have MAS (ABC) and NW (QMSI) SOW's out to contracting (Zaine) for review and once approved from there they can start getting negotiated with vendors, the plan is to have the PO out by Oct 15th. Currently GA (QMSI) SOW is being reviewed by few of us and should be out to contracting as well. We should have OH & HI (ABC) SOW out for review early next week, the intent for these is to get PO's out by Oct 30th. | Thangamani X. Vaiyapuri | 2011-12-01 11:53 | Thangamani X. Vaiyapuri | No |  | sites/OPPR/Sprints/Lists/Technology Team Issues Log
7 | Availability of environment to support WPP development/testing | 19007-ESB Sprints | 2011-12-01 11:26 | 2011-12-15 | WPP | Medium | Active | Nasir Ahmad Karamat |  | No | No | Yellow |  | WPP and OPPR timelines for delivery, testing and deployment may not match. | This needs constant coordination with WPP team | 9/22/2011: WPP plan shows the WPP Front end UI available only by Feb 2011 for OPPR QSG to perform intergration testing. This is a potential risk.. Teams working with environment team for quicker installation of ESB components. Test data and environments discussion with WPP in progress. Escalated to PMO. WPP Team needs to complete development of WPP components so that end to end connectivity (WPP -> ESB -> Stores) can be tested. ESB Dev teams are testing with Soap UI without WPP part (meaning ESB-> Stores) as work around. But for QA testing, WPP is mandatory as they don’t test with Soap UI. 9-20 gvk - # The OPPR and WPP teams have jointly met with the NCAL KPHC team last Friday and again this Tuesday, and made progress toward identifying two instances including the North Bay instance and the Central Valley instance in the WITS3 KPHC environment in NCAL to be available for OPPR-WPP interface testing # Similarly we met with the SCAL KPHC team and identified the RESC environment that will be available for OPPR-WPP interface testing. Had initial meeting with the SCAL KPHC environments team on 9/7/11 and with the NCAL KPHC environments team on 9/16/11 alongwith WPP team members to discuss environment availability for WPP-OPPR testing. Good progress made during the meeting. Identifying dates when the RESC environment in SCAL and the WITS3 environment in NCAL will be available for WPP-OPPR testing. | Thangamani X. Vaiyapuri | 2011-12-01 11:26 | Thangamani X. Vaiyapuri | No | 10/31: This is applicable for both WPP and ePIMS. WPP Team needs to complete development of WPP components. ePIMS: Need stores for all regions so that we can complete testing from ESB to EPS Stores thru Soap UI. We have stores for SCAL and NCAL so far. ESB Team is currently testing for SCAL stores and Next sprint we will be doing NCAL testing. We need stores for ROC1 and ROC2. 10/24: WPP team will provide a status update by the end of the week. | sites/OPPR/Sprints/Lists/Technology Team Issues Log
8 | Unknown ESB Scope of Changes for KPHC Summer 10 Changes | 19007-ESB Sprints | 2011-12-01 11:29 | 2011-12-23 | Ext Dependency | Medium | Active | Neeraj Pandey |  | No | No | Yellow | None required. Information only at this point for OPPR Exec Mgmt. | Resolving end date issues for Summer 10 release for KPHC NCAL/SCAL | OPPR needs to work with KPHC team and synchronize the end dates and manage dependencies. | 10/20: KPHC should provide more details on scope of changes, schedule etc so that ESB related changes can be identified and scheduled on sprint cycle. Required to know leadership direction on the target release of the change. | Thangamani X. Vaiyapuri | 2011-12-01 11:29 | Thangamani X. Vaiyapuri | No | 10/28: Scope of ESB changes, Timeline and Target Releases are Unknown. Next meeting with Lisa Sivak/KPHC is scheduled on 11/4 to follow up | sites/OPPR/Sprints/Lists/Technology Team Issues Log
9 | DEA Certification - Requirements and Design not ready - Impacting SCAL Timelines | 19007-ESB Sprints | 2011-12-01 11:31 | 2011-12-23 | DEA | Medium | Active | Neeraj Pandey |  | No | No | Green | None required. Information only at this point for OPPR Exec Mgmt. | DEA CA regulation is to address eprescription for controlled substances. This is one of the deliverables from a SCAL Rel 1 perspective and needs to go to the issues list. | The folow-up from the team will include: Details on the DFA from KPHC - what is Epic/KP planning on doing for DFA? I will escalate this to the regional KPHC contacts (NCAL/SCAL/GA/..) today. What is the timeline for this within KP? We need to align ourselves with the overall KPHC timelines. From a PDX point of view, we need to look into: What is PDX pursuing for the other customers? What is the timeline for PDX delivery? What certification (federal/regional) is PDX planning on pursuing towards the certification process? Thanks for bringing this up, Toni. Is the DFA configurable within PDX land? Once KP comes with the DFA tokens, what is the timeline for PDX delivery to ensure that it meets the regional/federal statutes for all the KP regions? | -This is likely to have funding impact as well.. | Thangamani X. Vaiyapuri | 2011-12-01 11:31 | Thangamani X. Vaiyapuri | No | 10/28: Scope Issues are getting resolved. Still some more questions need answers. Next meeting is scheduled on 11/4. All the questions must be resolved in next couple of weeks, so that PO and Sanath should be able to write USs for PDX | sites/OPPR/Sprints/Lists/Technology Team Issues Log
11 | KP IT needs to approve QMSI hardware purchase | 19007-ESB Sprints | 2011-12-01 11:46 | 2011-12-23 | SBMO | Medium | Active | Neeraj Pandey |  | No | No | Yellow |  | QMSI has given list of hardware for KP to procure. KP IT needs to approve hardware purchase. | 10/13: Arch and Gov- team to review and approve the hardware requirement. |  | Thangamani X. Vaiyapuri | 2011-12-01 11:46 | Thangamani X. Vaiyapuri | No |  | sites/OPPR/Sprints/Lists/Technology Team Issues Log
4 | Defining Build Completion Dates for New Env such as QA2 and UAT | 19007-ESB Sprints | 2011-12-01 08:57 | 2011-12-30 | Environments | Medium | Active | Jeffrey Raymond Poole |  | No | No | Green |  | The ESB Build completion dates should be aligned with actual env usage. FOr example, the UAT will be used only during March 2012 timeframe. | Need to build comprehensive build dates Need to identify dedicated resources and communicate the same to all |  | Thangamani X. Vaiyapuri | 2011-12-01 08:57 | Thangamani X. Vaiyapuri | No |  | sites/OPPR/Sprints/Lists/Technology Team Issues Log
5 | Need to use Mock inventory services for QSG | 19007-ESB Sprints | 2011-12-01 11:21 | 2011-12-30 | Inventory | Medium | Active | Jeffrey Raymond Poole |  | No | No | Yellow |  | PDX has completed 95% work. Onelink is done about 70% of work and ESB team has 6 sprints worth of work. | ESB team to help with Mock services | 11/14: Per Ravi's Email: As we start testing, Inventory team needs help from Development team until OneLink is ready to test. GC, Neeraj, Ravi from Rx BIO are meeting with Steve Stock, Michelle Wright and Ashok Vijay on November 22nd to arrive at timeline that will be workable for both teams. 9/21: Ravi's Email I am glad to see you brought this to my attention. Mock Inventory service needs to be provided by Neeraj's team during testing when OL is not fully ready.. Neeraj, Can you please let Mani know how you plan to support this during testing? Ravi and Neeraj to meet | Thangamani X. Vaiyapuri | 2011-12-05 11:41 | Thangamani X. Vaiyapuri | No | 10/28: Per Neeraj, meeting is scheduled w/ Vendor on 12/28 to discuss the team readiness for this activity 10/20: Per Neeraj, one of new CSC teams will be involved to complete this work. Need to work on Schedule | sites/OPPR/Sprints/Lists/Technology Team Issues Log
12 | Automed regions - MAS, OH, HI- cost of hardware has been included as part of the contract. | 19007-ESB Sprints | 2011-12-01 11:47 | 2011-12-30 | SBMO | Medium | Active | Neeraj Pandey |  | No | No | Yellow |  | Automed regions - MAS, OH, HI- cost of hardware has been included as part of the contract. | 10/13: Automed does not want KP to procure hardware. This could be a breach of contract. Neeraj and Tariq to take action. |  | Thangamani X. Vaiyapuri | 2011-12-01 11:47 | Thangamani X. Vaiyapuri | No |  | sites/OPPR/Sprints/Lists/Technology Team Issues Log
6 | Onelink to provide development time lines. | 19007-ESB Sprints | 2011-12-01 11:24 | 2011-12-30 | Inventory | Medium | Active | Sriram X. Ranganathan |  | No | No | Yellow |  | Inventory end to end testing cannot be done without Onelink delivering. | 9/20/2011: Ravi's Email:Waiting on OneLink to provide this. Will let you know as soon as we hear from them. Work with Onelink team | 12/05: Sriram is working with Debi to finalize the schedule 11/14: Per Ravi's Email, GC, Neeraj, Ravi from Rx BIO are meeting with Steve Stock, Michelle Wright and Ashok Vijay on November 22nd to arrive at timeline that will be workable for both teams. 10/28:Sriram and Ravi are working w/ OneLink - NO ETA Ravi to work on meeting with Onelink 10/20: Ravi to provide latest status on this issue. Changed the due date to 10/28 | Thangamani X. Vaiyapuri | 2011-12-05 11:42 | Thangamani X. Vaiyapuri | No |  | sites/OPPR/Sprints/Lists/Technology Team Issues Log
18 | getPatientPCP service does not have credential access to KPHC hence cannot perform the PCP lookup. | 19007-ESB Sprints | 2011-12-01 13:40 | 2011-12-31 |  | Medium | Active | Ashish Tengshe |  | No | No | Green |  | getPatientPCP service does not have credential access to KPHC hence cannot perform the PCP lookup. |  |  | Thangamani X. Vaiyapuri | 2011-12-01 13:40 | Thangamani X. Vaiyapuri | No |  | sites/OPPR/Sprints/Lists/Technology Team Issues Log
27 | SCAL Cutover and Dry Runs begin 3/28 | xxxxx-Prod Support | 2012-01-20 11:46 | 2012-01-20 | Go-Live | Medium | Active | Jeffrey R. Poole | Ashish D. Tengshe | No | No | Yellow |  | SCAL Cutover Dry Runs begin 3/28. There are no resources identified to perform the Dry Runs and SCAL go-lives. Will this be TCS? Will this be CSC? Was this addressed with Ash's latest trip to India? | tbd | 1/20 JP | Jeffrey Raymond Poole | 2012-01-20 11:46 | Jeffrey Raymond Poole | No |  | sites/OPPR/Sprints/Lists/Technology Team Issues Log
28 | CSC Off-Shore Contract | xxxxx-Prod Support | 2012-01-20 11:49 | 2012-01-24 | Resources | Medium | Active | Jeffrey R. Poole | Ashish D. Tengshe | No | No | Yellow |  | Two ESB engineers that were hired at Offshore, post KP interview, are already on board and are waiting in the wings to start work. One option could be to start them on WO till Environment and Development SOW gets signed. From Vishal Prakash <vprakash3@csc.com> via Jeremy | tbd | 1/20 JP | Jeffrey Raymond Poole | 2012-01-20 11:49 | Jeffrey Raymond Poole | No | 1/20 - Need to discuss with Ash, Jeremy and Neeraj | sites/OPPR/Sprints/Lists/Technology Team Issues Log
23 | ESB1 - DEPENDENCY OF ESB STORIES ON PDX DELIVERABLES | 19007-ESB Sprints | 2012-01-12 17:05 | 2012-01-27 |  | Medium | Active | Neeraj Pandey |  | No | No | Green |  | DEPENDENCY OF ESB STORIES ON PDX DELIVERABLES: Completion of the following 8 development ESB user stories (40% of 20 development stories committed in Cycle 33 at RISK, or 37 points of a total of 113 development story points or 33% development story points at RISK! ). They are at RISK because they are dependent on PDX delivering their Cycle 33 code early in Cycle 33 versus at the end of Cycle 33: - Expanding correlation Id US6645 - 5 points US6642 - 8 points - Single use flag for address, phone and email US6652 - 5 points US6627 - 5 points US6625 - 5 points - Mailability being returned in select patient response US6622 - 3 points US6621 - 3 points US6619 - 3 points. To be very blunt, when we have had to work with PDX in parallel, our experience has been nothing but disappointing, primarily because they have delivered the WSDL and code that we needed to work with, not at the beginning or middle of the Cycle to allow us to work with their code, but they have delivered it at the end of the Cycle, thereby not allowing the ESB team to do their coding before the Cycle end. However, on Monday 01/09/12, we have already asked them for the new WSDL for Cycle 33, to allow us to begin our work. We will still need their code as soon as possible during Cycle 33, so that we can do our testing with their code. |  |  | Thangamani X. Vaiyapuri | 2012-01-12 17:05 | Thangamani X. Vaiyapuri | No |  | sites/OPPR/Sprints/Lists/Technology Team Issues Log
24 | ESB1 - UNSTABLE / CHANGING ENVIRONMENTS | 19007-ESB Sprints | 2012-01-12 17:06 | 2012-02-03 |  | Medium | Melva Jeter | Jeffrey Raymond Poole |  | No | No | Green |  | UNSTABLE / CHANGING ENVIRONMENTS: - this has been a concern for sometime now, and we continue to face environment downtime and environments changing issues for one reason or the other. The situation has not changed much, as environments go down and are changed more frequently than we would prefer. Every time an environment changes occur for whatever reason, our developers and testers have been asked to test and validate the environment. |  |  | Thangamani X. Vaiyapuri | 2012-01-12 17:06 | Thangamani X. Vaiyapuri | No |  | sites/OPPR/Sprints/Lists/Technology Team Issues Log
22 | Need additional Testing Resources for ESB1 and ESB5 Teams | 19007-ESB Sprints | 2012-01-12 17:02 | 2012-02-03 |  | Medium | Active | Neeraj Pandey |  | No | No | Green |  | Teams are running short of testing resources |  |  | Thangamani X. Vaiyapuri | 2012-01-12 17:02 | Thangamani X. Vaiyapuri | No |  | sites/OPPR/Sprints/Lists/Technology Team Issues Log
14 | LED Display POC - Need Architectural Direction | 19007-ESB Sprints | 2011-12-01 11:50 | 2011-12-02 | ESB 5 - LED Display POC | Select One | Active | Pattabi X. Venkatesan |  | No | No | Green |  | Need Architectural direction for completing POC for LED display in Windows env. |  | 11/14: Per Pattabi's email - The new monitor is being set up in the lab -- Once its ready, we'll complete the POC and publish findings / recommendations. | Thangamani X. Vaiyapuri | 2011-12-01 11:50 | Thangamani X. Vaiyapuri | No | 11/14: Per Pattabi's email - The new monitor is being set up in the lab -- Once its ready, we'll complete the POC and publish findings / recommendations. 10/28: No update | sites/OPPR/Sprints/Lists/Technology Team Issues Log